## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing. | Test results | Initials of Testers
2185-swen-14-261-c Avoiding Zuggzwang
Start a Game (13) | **Given** that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | pass! 2/24 | EN, AB, CB, TK, JJ
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | pass! 2/24 | EN, AB, CB, TK, JJ
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | pass! 2/24 | EN, AB, CB, TK, JJ
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the _Game View_ as the White player. _NOTE_: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | pass! 2/24 | EN, AB, CB, TK, JJ
| Given a valid, initial game board whenI drag a piece to a white space then the piece should not be _droppable_. | pass! 2/24 | EN, AB, TK
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | pass! 2/24 | EN, Ab, TK, CB
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the _Game View_ as the White player. _NOTE_: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | pass! 2/24 | AB, TK, JJ
Player Sign-in (8) | Given that I have not signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | pass! 2/24 | AB, CB, EN, TK, JJ
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | pass! 2/24 | AB, CB, EN, TK, JJ
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | pass! 2/24 | AB, CB, EN, TK, JJ
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | pass! 2/24 | AB, CB, EN, TK, JJ
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the **Sign-in** button then I expect the system to reject my sign-in and return the Sign-in page with a message for me to try another name. | pass! 2/24 | AB, CB, EN, TK, JJ
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all the other signed-in players who are available to play a game. (_NOTE_: in the next story you will use this list to pick opponents for checkers games.) | pass! 2/24 | AB, CB, EN, TK, JJ
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all the other signed-in players who are available to play a game. (_NOTE_: in the next story you will use this list to pick opponents for checkers games.) | pass! 2/24 | AB, CB, TK
| Given that I am _not_ signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | pass! 2/24 | TK, CB, JJ
END OF SPRINT 1 SPRINT TWO BEGINNING
Sign out (3) | **Given** that I am on the sign out page when I confirm my decision to sign out **then** I expect to be returned to the pre-sign in home page. | PASS! 3/26 | EN, AB
| **Given** that I am on the sign out page **when** I confirm that I want to sign out **then** I expect my data to be removed from the server. | PASS! 3/26 | EN, AB, TK
| **Given** I am signed in as a player **when** click a 'sign out' link **then** I expect to be taken to a page where I can confirm my choice to sign out. | PASS! 3/26 | EN, AB
Resignation (5) | Given I'm in a game when I resign then I expect my opponent to win. | PASS! 3/26 | EN, AB, TK, CB, JJ
| *Given* I'm in a game *when* my opponent resigns *then* I expect to win. | PASS! 3/26 | EN, AB, TK CB JJ
| Given that I am in a game when either player resigns then I expect to be returned to the home page. | PASS! 3/26 | EN, AB, TK CB JJ
Simple Moves (8) | Given I’m in a game when it is not my turn then I expect that my piece will not move | PASS! 3/27 | EN, TK, CB
| Given it is my turn when I move to an invalid spot, then I expect my piece will not move | PASS! 3/27 | EN, TK, CB
| Given I'm in a game when I move my piece to a valid space then I expect my piece to move to the given location. | PASS! 3/27 | EN, TK, CB
| Given that my piece is not a King when I make a simple move then I expect to only be able to move one space diagonally forward | PASS! 3/27 | EN,TK,CB
Single Jump (5) | Given I’m in a game and it is my turn, when I jump over a piece, then I expect to capture that piece | Pass 3/27 | CB,EN,TK
| Given I’m in a game and it is not my turn, when I jump over a piece, then I expect the move to not happen | PASS 3/27 | CB, EN, TK
Out of Pieces (8) | **Given** a player is in a game **when** their last piece is captured then I expect the game to end. | Incomplete Testing, and logic not moved in. Decided to complete the project rather than move on with implementing this story
| Given I am a player when I capture the last piece and submit the move then I expect a win. | Incomplete Testing, and logic not moved in. Decided to complete the project rather than move on with implementing this story
Given that I am in a game When I lost my last peice to either a regular jump or a super mega death jump then i expect to lose
Super Mega Jump of Death (8) | Given I am in a game and it is my turn, when I leap over multiple pieces, then I expect to capture all of those pieces | PASS 3/27 | CB, EN, TK
| Given I am in a game and it is my turn, when I try to leap over multiple pieces invalidly, then I expect the move not to happen | PASS 3/27 | CB, EN, TK
King Me (3) | Given I am in a game, when I reach the end of the board, then I expect that piece to become a king | PASS 3/27 | TK, EN, AB
| Given I am in a game and have a king piece, when I move that king piece, I expect that piece to be able to move backwards | PASS 3/27 | TK, EN, AB
END OF SPRINT TWO SPRINT THREE BEGINNING
Finish Multi-Jump Validation (3) | Given I have started a multi-jump, when I attempt to submit without finishing the jump, I should see an error | Pass 4/10 | TK, EN, CB
| Given I have completed a multi-jump, when I attempt to submit the finished multi-jump, then I expect the move to be valid | Pass 4/10 | TK, EN, CB
Out of moves (5) | **Given** that i am a player **when** my opponent or I cannot make a move **then** I EXPECT the game to end. | Pass 4/10 | TK,EN,CB
| **Given** that the game ends **when** either player cannot make a move **then** I EXPECT the player who moved last to be the winner. | Pass 4/10 | TK,EN,CB
| **Given** that I am a player **when** it is my turn and I have available moves **then** I EXPECT the game to continue as normal | Pass 4/10 | TK,EN,CB
| **Given** that the game ends **when** either player cannot make a move **then** I EXPECT the players to be informed that the game is over and who won. | Pass 4/10 | TK,EN,CB
AI Move (5) | **Given** I play against AI **when** when the AI takes its turn **then** I expect the AI to follow the same rules
**Give** I play against an AI **when** it is its turn **then** I expect it to make a jump move when posible
Save Replay (3) | **Given** that I am in a game **when** it ends **then** I expect the server to save that game so that it can be watched latter
Enter Replay mode (5) | **Given** I am in the menu **when** I click enter replay mode **then** I EXPECT to be in replay mode and see my saved games.
Given that there is a replay saved when i click on replay mode then I expect to see a list of all the saved games
Watching Replay Mode (5) | **Given** I am in replay mode **when** I click on the next move button **then** I EXPECT to be able to see the result of the next turn.
Given I am in replay mode, when I click on the back up move button, then I expect to be able to see the previous state of the game
Forcing Jumps (5) | Given when I attempt to submit a simple turn when a jump is possible then I expect an error message | Pass 4/10 | TK,EN,CB
|  | Pass 4/10 | TK,EN,CB
Out of Pieces (8) | **Given** a player is in a game **when** their last piece is captured **then** I expect the game to end. | Pass 4/10 | TK,EN,CB
| **Given** **when** I capture the last piece and submit the move *then* I expect a win. | Pass 4/10 | TK,EN,CB
| **given** that I am in a game **When** I lost my last peice to either a regular jump or a super mega death jump **then** i expect to lose | Pass 4/10 | TK,EN,CB

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button)
Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name.
Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page.
Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.)
Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name.
Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all.
Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page.
Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.)
Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons).
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page.
Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player.
Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message.
Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game.
Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories.
Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world.